## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | Car Inventory System |  |  |  |  | GROUP NUMBER | [8 empty] | 3
INSTRUCTOR |  | Engr. Roy Vincent Marañon |  |  |  |  | DATE | [8 empty] | Sept. 22, 2018
[7 empty] | PHASE ONE |  |  |  | PHASE TWO |  |  | PHASE THREE | [5 empty] | PHASE THREE |  |  |  | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | Week 3 |  |  |  | WEEK 4
[7 empty] | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED
1 | Conception
1.1 | Requirements Research | Mary Jane Gelasque & Zeny Tricia Dagcuta | 09/17/2018 | 09/17/2018 | 1 | 100% | bar: WEEK 1 MON
1.2 | Revisions of Researched Projects | Cqaer Codilla and Jay Ann Diocampo | 09/18/2018 | 09/18/2018 | 1 | 100% | bar: WEEK 1 TUE
1.3 | Project Guidelines | Earl Regner and James Teves | 09/19/2018 | 09/19/2018 | 1 | 100% | bar: WEEK 1 WED
1.4 | Project Initiation | Jocar Alfred Conol and Gee Rey Espino | 09/20/2018 | 09/20/2018 | 1 | 100% | bar: WEEK 1 THU
2 | Planning
2.1 | Requirement Giving | James Teves and Aaron Brent Abundo | 09/21/18 | 09/21/18 | 1 | 100% | bar: WEEK 1 FRI
2.2 | Communication Plan and Risk Management | James Teves and Aaron Brent Abundo | 09/22/18 | 09/22/18 | 1 | 100% | bar: WEEK 1 SAT
2.3 | Project Flow Planning | Jocar Alfred Conol and Gee Rey Espino | 09/23/18 | 09/23/18 | 1 | 100% | bar: WEEK 1 SUN
2.4 | Astah Creation | James Teves and Earl Regner | 09/23/18 | 09/23/18 | 1 | 100% | bar: WEEK 1 SUN
3 | Launch and Execution
3.1 | Designing of UI |  | 09/24/18 | 09/25/18 | 2
3.1.1 | .XAML Ui designing of Dashboard | James Teves and Earl Regner | 09/24/18 | 09/25/18 | 1 | 100% | bar: WEEK 2 MON to WEEK 2 TUE
3.1.2 | .XAML Ui designing of Inventory | Cqaer Codilla and Jay Ann Diocampo | 09/24/18 | 09/25/18 | 1 | 100% | bar: WEEK 2 MON to WEEK 2 TUE
3.1.3 | .XAML Ui designing of Cart | Mary Jane Gelaque and Zeny Tricia Dagcuta | 09/24/18 | 09/25/18 | 1 | 100% | bar: WEEK 2 MON to WEEK 2 TUE
3.1.4 | .XAML Ui designing of window 2 | Jocar Alfred Conol and Gee Rey Espino | 09/24/18 | 09/25/18 | 1 | 100% | bar: WEEK 2 MON to WEEK 2 TUE
3.2 | Declaration in CS file |  | 09/26/18 | 09/27/18 | 2 | bar: WEEK 2 MON to WEEK 2 TUE
3.2.1 | Hyundai 15 Hyundai cars +4 mitsubishi cars | Cqaer Codilla and Jay Ann Diocampo | 09/26/18 | 09/27/18 | 1 | 100% | bar: WEEK 2 WED to WEEK 2 THU
3.2.2 | Suzuki 15 Suzuki cars +4 mitsubishi cars | Earl Regner and James Teves | 09/26/18 | 09/27/18 | 1 | 100% | bar: WEEK 2 WED to WEEK 2 THU
3.2.3 | Ford 15 Ford cars +4 mitsubishi cars | Jocar Alfred Conol and Gee Rey Espino | 09/26/18 | 09/27/18 | 1 | 100% | bar: WEEK 2 WED to WEEK 2 THU
3.2.4 | Honda 15 Honda cars +4 mitsubishi cars | Mary Jane Gelasque and Zeny Tricia Dagcuta | 09/26/18 | 09/27/18 | 1 | 100% | bar: WEEK 2 WED to WEEK 2 THU
3.3 | Assigning of Functions | Aaron Brent Abundo | 09/28/18 | 09/28/18 | 1 | 100% | bar: WEEK 2 FRI
3.4 | Monitoring | James Teves and Aaron Brent Abundo | 09/29/18 | 09/29/18 | 1 | 100% | bar: WEEK 2 SAT
3.5 | Resourcing | James Teves and Earl Regner | 09/29/18 | 09/29/18 | 1 | 100% | bar: WEEK 2 SAT
4 | Testing and Debugging
4.1 | Full Testing with Test Specifications | Cqaer Codilla and Jay Ann Diocampo | 09/30/18 | 09/30/18 | 1 | 100% | bar: WEEK 2 SUN
4.2 | First Testing and debugging | Aaron Brent Abundo | 09/30/18 | 09/30/18 | 1 | 100% | bar: WEEK 2 SUN
4.3 | Second Testing and Debugging | James Teves | 2018-01-10 | 2018-01-10 | 1 | 100% | bar: Week 3 MON
4.4 | Last Testing and Debugging | Cqaer Codilla and Jay Ann Diocampo | 2018-02-10 | 2018-02-10 | 1 | 100% | bar: Week 3 TUE
4.5 | Project Presentation | All Involved | 2018-03-10 | 2018-03-10 | 1 | 100% | bar: Week 3 WED
CLICK HERE TO CREATE WBS TEMPLATES WITH GANTT CHART IN SMARTSHEET

## WBS with Gantt Chart BLANK (hidden)
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 20%
100%
90%
40%
70%
60%
50%
100%
30%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET